## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 14
PROJECT NAME | Bard API Integrated with HTML UI
PROJECT MENTOR (sponsor) | Patenti Technology Solutions
TEAM MEMBERS | Harshit Gupta
Ayush Sahu
Rahul Singal
Divyansh Pandey

## Status
PROJECT NUMBER | 14
PROJECT NAME | Bard API Integrated with HTML UI
PROJECT MENTOR (sponsor) | Amrutha Moorthy(Patenti Technology Solutions)
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | TA | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
GIT Repository setup | Preparation | TA | 1 | 1.5 | Done |  | -0.5 | 33.3333
Client meeting | Coordination | Entire Team | 1 | 1 | Done | Make sure scoping questions are included | 0 | 0
Research existing technology | Preparation | Entire Team | 2 |  | Ongoing
Project synopsis writeup | Documentation | Harshit | 1 | 0.5 | Done |  | 0.5 | 100
Identify role owners | Preparation | Entire Team | 1 | 0.6 | Done | Multiple roles are OK - think about role & reponsibility distribution | 0.4 | 66.6667
Team Meeting | Coordination | Harshit | 1 | 2 | Done | Discussed Division of Work, completed project synposis | -1 | 50
Status tracker | Documentation | Rahul | 0.5 | 0.5 | Done |  | 0 | 0
Week 2 (January 22 - January 28)
Learn Django | Preparation | Rahul,Harshit | 4 |  | Ongoing
BARD API research of literature | Preparation | Divyansh | 4 |  | Ongoing | This is critical to project success
Develop questions for requirements elicitation | Documentation | Entire Team | 1 | 2 | Done | Make sure scoping questions are included | -1 | 50
Get account and configure website | Preparation | Entire Team | 1.5 |  | Planned
Team Meeting | Coordination | Entire Team | 1 | 1 | Done | Discussed Project Plan | 0 | 0
Status tracker | Documentation | Rahul | 0.5 | 0.5 | Done | Pushed into repo | 0 | 0
Project Plan | Documentation | Harshit,Rahul,Divyansh | 1 | 1 | Done | Sent to Client | 0 | 0
Bootstrap Research of Literature | Preparation | Ayush | 4 |  | Ongoing
Week 3 (January 29 - February 4)
Client meeting | Coordination | Entire Team | 1 | 1 | Done | Discussed project plan, discussed need to divide subtasks, | 0 | 0
BARD API research of literature | Preparation | Divyansh | 4 |  | Ongoing
Learning BootStrap | Design | Rahul | 3 | 5 | Done |  | -2 | 40
HTML/CSS Files Created | Design | Rahul,Ayush | 0.5 | 0.5 | Done | Starter Files Created
Django Starter Files Created | Design | Rahul,Harshit | 0.5 | 1 | Done | Starter Files Created
Week 4(February 5 – February 11)
Database Basic Layout | Design | Harshit | 1 | 1 | Done | Basic Design of the database is created | 0 | 0
Frontend Design Work | Design | Rahul,Ayush | 7 |  | Ongoing
Week 5(February 12-February 18)
Landing Page Design | Design | Rahul | 1 |  | Ongoing | Designing using HTML,Bootstrap,JS left
Login and Registration Page Design | Design | Rahul | 2 |  | Ongoing | Designing using HTML,Bootstrap,JS left
Chatbot page design | Design | Ayush | 3 |  | Ongoing | Designing using HTML,Bootstrap,JS left
Linking of registration page and landing page | Design | Harshit | 2 | 4 | Done | Added GET and POST request links
SRS document creation | Documentation | Entire Team | 2 | 1.5 | Done |  | 0.5 | 33.3333
Client meeting | Coordination | Entire Team | 1 | 0.75 | Done
Progress on BARD and cookie management | Development | Divyansh | 5 |  | Ongoing
Week 6(February 19-February 25)
Test Plan Tracker creation | Documentation | Entire Team | 3 | 4.5 | Done | Created test cases for various use cases | -1.5 | 33.3333
Landing Page Design | Development | Rahul | 1 | 1 | Done |  | 0 | 0
Login and Registration Page Design | Development | Rahul | 1 | 1 | Done |  | 0 | 0
Chatbot page design | Development | Rahul,Divyansh | 4 |  | Ongoing | Basic design done, JS addition left
Project Document Updation | Documentation | Rahul | 0.33 | 0.33 | Done | Updated the API,i.e. Gemini | 0 | 0
Progress on Gemini API | Development | Divyansh | 5 |  | Ongoing
Week 7(February 26 – March 3)
Chatbot page design | Development | Rahul,Divyansh,Ayush | 4 |  | Ongoing
Unit Testing | Testing | Entire Team | 4 |  | Ongoing | Testing out individual components
Integration Testing | Testing | Entire Team | 4 |  | Ongoing
Client meeting | Coordination | Entire Team | 1 | 0.5 | Done |  | 0.5 | 100
Integration of API | Interfaces | Divyansh,Harshit | 2 | 3 | Done |  | -1 | 33.3333
IP Address and Prompt Storage | Interfaces | Harshit | 2 | 2 | Done |  | 0 | 0
Week 8(March 4 – March 10)
Chatbot page integration | Development | Divyansh, Harshit | 10 |  | Ongoing
Client Meeting | Coordination | Divyansh, Ayush, Harshit | 1 | 0.33 | Done |  | 0 | 0
Design of Prompt History | Development | Divyansh | 4 |  | Ongoing | How the search history of the user will be displayed
User Details Storage | Interfaces | Harshit | 3 | 2 | Done |  | 1 | 50
Chatbot page Design | Development | Rahul, Ayush, Divyansh | 3 |  | Ongoing
Week 9(March 11 – March 17)
Chatbot page integration | Development | Divyansh,Harshit | 10 | 11 | Done |  | -1 | 9.0909
Design of Prompt History | Development | Divyansh | 4 | 5 | Done |  | -1 | 20
Chatbot page Design | Development | Rahul,Ayush,Divyansh | 3 | 5 | Done |  | -2 | 40
Testing of Various Components | Testing | Rahul,Ayush | 3 | 4 | Done | Tested various components in accordance with the test plan tracker | -1 | 25
Linting python files | Testing | Ayush | 3 | 2 | Done |  | 1 | 50
Client Meeting | Coordination | Entire Team | 1 | 0.33 | Done |  | 0.67 | 203.0303
Preparation of Presentation for R1 | Preparation | Entire Team | 3 |  | Ongoing
Week 10(March 18 – March 24)
Initiation of AWS research | Preparation | Rahul,Ayush | 6 |  | Ongoing
Research for Context filtering | Preparation | Divyansh,Harshit | 8 |  | Ongoing
Client Meeting | Coordination | Entire Team |  |  | Planned
Week 11(March 25-March 31)
AWS account creation | Preparation | Rahul | 1 | 0.33 | Done |  | 0.67 | 203.0303
AWS research | Preparation | Rahul,Ayush | 6 |  | Ongoing
Research for Context filtering | Preparation | Divyansh,Harshit | 8 |  | Ongoing
Week 12(April 1-April 7)
Initiation of Deployment | Development | Rahul,Ayush | 12 |  | Ongoing
Collection of sample data | Preparation | Divyansh,Harshit | 3 |  | Done
Research work | Preparation | Entire Team | 6 |  | Ongoing
Week 13(April 8-April 14)
Creation of Application using Codedeploy | Development | Rahul | 0.5 | 0.5 | Done |  | 0 | 0
Installing Codedeploy on EC2 instance | Development | Rahul | 0.5 | 0.5 | Done |  | 0 | 0
Configuring AWS Systems Manager | Development | Rahul | 0.5 | 0.5 | Done |  | 0 | 0
Troubleshooting Deployment | Development | Rahul,Ayush | 2 |  | Ongoing
Context Filtering Application | Development | Divyansh,Harshit | 6 |  | Ongoing
Week 14(April 15-April 20)
Context Filtering Application | Development | Harshit,Divyansh | 6 | 10 | Done |  | -4 | 40
Implementation of User Profile on Chatbot page | Development | Rahul | 2 | 1.5 | Done |  | 0.5 | 33.3333
Implementation of loading effect | Development | Ayush | 2 | 4 | Done |  | -2 | 50
Implementation of About Us Page | Development | Rahul | 2 | 3 | Done |  | -1 | 33.3333
Revision of Documents | Documentation | Rahul | 3 | 3 | Done |  | 0 | 0
Preparation of Test Cases | Delivery | Entire Team | 3 | 3 | Done |  | 0 | 0
Project Report (As required by Client) | Delivery | Entire Team | 3 | 4 | Done |  | -1 | 25
Demo Video (As required by client) | Delivery | Entire Team | 0.5 | 0.33 | Done |  | 0.17 | 51.5152
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically